Terra Vita FieldTrace Training Implementation Pack

Jazira Phase 0 — Capacity Building for Environmental Conservation

Implementation period: 18–28 July 2026 · Programme code: JAZIRA-SOM-2026

Current status Pre-mobilisation evidence accepted. FieldTrace intake prepared and configured. Training implementation evidence pending. Not funding-ready / not funding-cleared.

| Field | Confirmed value |
| --- | --- |
| Programme | Jazira Phase 0 — Capacity Building for Environmental Conservation |
| Programme code | JAZIRA-SOM-2026 |
| Implementer | AECBED |
| Evidence owner | Sabir Ibrahim |
| Backup owner | Abdinasir Sheikh Mohamed Hassan |
| Terra Vita role | FieldTrace intake, evidence architecture, reviewer QA, Hub linkage |
| Hub status | Accepted for Phase 0 pre-mobilisation reviewer record; not funding-ready / not funding-cleared |

# 1. Purpose of this pack

This pack prepares the Jazira Phase 0 training implementation cycle so that the 18–28 July 2026 evidence is captured daily, bound to FieldTrace, and linked back to the Terra Vita Hub reviewer record. It is intended for AECBED facilitators, field operators, reviewers and Terra Vita governance QA.

Authority boundary This training implementation pack does not approve funding, certify the programme, make Jazira donor-ready, or clear any funding decision. It prepares the controlled evidence pathway only. Funding readiness remains a separate Terra Vita reviewer decision after implementation evidence, QA, MoIFAR renewal and follow-up evidence are complete.

# 2. Training objectives and outputs

| Objective | Required output | FieldTrace category |
| --- | --- | --- |
| Train community participants in conservation and resilience basics | 60 participants trained; attendance and session evidence | FT-02 / FT-03 |
| Track inclusion and participation | Gender, youth and IDP-household fields in participant register; target ≥40% women participation | FT-01 / FT-02 |
| Measure knowledge gain | Pre-training baseline and post-training survey results | FT-04 / FT-05 |
| Prepare local trainers | 15 ToT scorecards / competency forms | FT-06 |
| Complete field practicum evidence | Geotagged photographs, field notes and operator records | FT-07 |
| Develop community conservation action plans | Six action plans with clear owners, actions, dates and evidence requirements | FT-08 |
| Document local/government support | Endorsement records from relevant local or government actors | FT-09 |
| Create reviewer reconstruction trail | Daily notes, final summary and follow-up pathway | FT-10 / FT-11 / FT-12 |

# 3. FieldTrace binding requirements

| Required field | Instruction |
| --- | --- |
| Programme | Use JAZIRA-SOM-2026 on every item. |
| Phase | Use Phase 0. |
| Site | Select Green Paradise Hotel, Jazira National Park field-practicum site, or Adjacent communities / Jaziira area. |
| Task category | Use FT-01 to FT-12 according to the evidence type. |
| Operator | Name the AECBED facilitator or field staff responsible for capture. |
| Timestamp | Record the date and, where possible, the time of activity/capture. |
| Location/GPS | Required for field practicum evidence and photos. Jazira National Park reference: Lat 1.959407, Long 45.186964. |
| Payload | Attach the evidence object: register, photograph, survey, scorecard, action plan, endorsement or note. |
| Consent status | Use consent confirmed, restricted internal review only, or pending. |
| Hub linkage | Evidence must link back to the Jazira Hub reviewer record. |

Naming rule Use: JAZIRA-SOM-2026-P0_[DATE]_[SITE]_[TASK]_[EVIDENCE-TYPE]_[OWNER]. Example: JAZIRA-SOM-2026-P0_2026-07-18_Green-Paradise_Attendance_Register_Sabir-Ibrahim.pdf

# 4. Implementation schedule

| Date | Day | Training focus | Core evidence to capture | FieldTrace |
| --- | --- | --- | --- | --- |
| 18 Jul | Day 1 | Programme orientation, consent, participant registration and baseline survey | Participant register; consent status; attendance; pre-training baseline | FT-01, FT-02, FT-04 |
| 19 Jul | Day 2 | Coastal, dry-forest and mangrove ecosystem fundamentals | Attendance; session notes; photos where consented | FT-02, FT-03 |
| 20 Jul | Day 3 | Reforestation and mangrove/coastal restoration practice | Attendance; session notes; practical learning evidence | FT-02, FT-03 |
| 21 Jul | Day 4 | Land, soil, water and ecosystem-risk management | Attendance; session notes; group exercises | FT-02, FT-03 |
| 22 Jul | Day 5 | Community livelihoods, inclusion and conservation-compatible activities | Attendance; inclusion notes; group work | FT-02, FT-03 |
| 23 Jul | Day 6 | Governance, local responsibility mapping and evidence discipline | Attendance; responsibility map notes; FieldTrace briefing | FT-02, FT-03, FT-10 |
| 24 Jul | Day 7 | Training-of-Trainers methods and facilitation practice | Attendance; ToT practice notes; draft scorecards | FT-02, FT-06 |
| 25 Jul | Day 8 | Post-training survey, ToT assessment and action-plan preparation | Post survey; ToT scorecards; action-plan group formation | FT-05, FT-06, FT-08 |
| 26 Jul | Day 9 | Field practicum at Jazira National Park | Geotagged photos; field notes; attendance; GPS-linked evidence | FT-07 |
| 27 Jul | Day 10 | Community action-plan development and validation | Action-plan drafts; community notes; daily note | FT-08, FT-10 |
| 28 Jul | Day 11 | Final action plans, endorsements and implementation summary | Six action plans; endorsements; final summary; evidence index | FT-08, FT-09, FT-11 |

# 5. Daily facilitator workflow

Morning setup: Confirm site, session topic, facilitator, participant list, consent posture, required forms and FieldTrace task category before the session starts.

During session: Capture attendance, session notes and photographs only where consent is confirmed. Avoid undocumented claims or retrospective reconstruction.

End of day: Prepare a daily evidence bundle: attendance, session note, photos if any, issues/deviations, operator name and next-day actions.

Reviewer discipline: Any missing, unclear or inconsistent evidence should be flagged the same day as clarification required rather than corrected silently.

# 6. Evidence categories and minimum acceptance test

| Code | Evidence category | Minimum acceptance test |
| --- | --- | --- |
| FT-01 | Participant nomination | Includes participant identity fields, category fields, eligibility basis and consent status where required. |
| FT-02 | Daily attendance | Signed or otherwise attributable; date, site, session and facilitator are clear. |
| FT-03 | Training sessions | Session notes identify topic, facilitator, date, location and key activities. |
| FT-04 | Pre-training baseline | Survey captured before training content is delivered. |
| FT-05 | Post-training survey | Post survey captured after classroom training; can be compared to baseline. |
| FT-06 | ToT scorecards | Each ToT candidate has an attributable scorecard or competency form. |
| FT-07 | Field practicum | GPS/location, date, operator, site and activity are visible; photos are not generic. |
| FT-08 | Action plans | Six plans identify community issue, proposed action, owner, timeline and support required. |
| FT-09 | Endorsements | Endorsement source, date and scope are clear. |
| FT-10 | Daily notes | Each day includes progress, deviations, issues and evidence captured. |
| FT-11 | Final summary | Summarises participants, outputs, evidence index, unresolved gaps and next steps. |
| FT-12 | Follow-up | 30/60/90-day reports identify continuation activity and evidence source. |

# 7. Roles and responsibilities

| Role | Responsible party | Responsibility |
| --- | --- | --- |
| Implementation lead | AECBED / Sabir Ibrahim | Coordinate training delivery, daily evidence capture and submission discipline. |
| Backup owner | Abdinasir Sheikh Mohamed Hassan | Support evidence continuity and unresolved escalations. |
| Facilitators | Named AECBED facilitators | Deliver sessions and ensure daily evidence is complete. |
| Terra Vita | Theresa / reviewer route | Confirm FieldTrace intake, review evidence and record Hub status. |
| Local authority / government actors | As applicable | Provide attendance or endorsement evidence where involved. |

# 8. QA and Hub status pathway

| Stage | Status | Meaning |
| --- | --- | --- |
| 1 | Received | Evidence has arrived but has not yet been checked for binding. |
| 2 | Bound | Evidence is linked to programme, site, task, operator, timestamp and payload. |
| 3 | Reviewer QA in progress | Terra Vita is checking sufficiency and traceability. |
| 4 | Accepted / clarification required / returned | Reviewer outcome is recorded per evidence item. |
| 5 | Implementation evidence received — reviewer QA in progress | Possible Hub status after the July pack is submitted. |

Funding-readiness boundary Do not describe Jazira Phase 0 as funding-ready, donor-ready or funding-cleared after training delivery alone. Funding-readiness review can only be considered after July implementation evidence, reviewer QA, MoIFAR renewal after 03 August 2026 and follow-up evidence pathway are complete.

# 9. Documents and templates issued with this pack

| Template | Use | FieldTrace category |
| --- | --- | --- |
| Participant Register | Nomination, eligibility and inclusion fields | FT-01 |
| Daily Attendance | Daily signed attendance register | FT-02 |
| Pre-Training Survey | Baseline knowledge and context capture | FT-04 |
| Post-Training Survey | Knowledge gain assessment | FT-05 |
| ToT Scorecard | Competency evidence for ToT graduates | FT-06 |
| Field Practicum Checklist | GPS-linked field evidence capture | FT-07 |
| Action Plan Template | Six community conservation action plans | FT-08 |
| Endorsement Record | Local/government endorsement evidence | FT-09 |
| Daily Implementation Note | Daily reconstruction trail | FT-10 |
| Final Implementation Summary | Post-training evidence summary and gaps | FT-11 |
| Follow-Up Tracker | 30/60/90-day continuation evidence | FT-12 |

# 10. Immediate actions before 18 July

Confirm final facilitator names and operator responsibilities.

Confirm final participant target list and inclusion tracking fields.

Confirm training language and whether translation/support is required.

Confirm local authority, MoECC or District Council attendance, if any.

Confirm who signs attendance, action plans and endorsement records.

Share the Training Evidence Templates workbook with AECBED and require daily capture.

Keep corrected PDFs/date inconsistencies and MoIFAR renewal as open Hub follow-up items.